{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["附表1","附表2","附表3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"附表1","index":0,"n_rows":16,"n_cols":8,"rows_kept":16,"merged":[[2,0,2,7],[5,0,7,0],[5,1,7,1],[5,5,10,5],[5,7,11,7],[8,0,10,0],[8,1,10,1],[11,0,11,1],[11,4,11,5],[12,0,12,7],[13,0,13,7],[14,0,14,7]],"flags":["formulas_cached_only"]}
[]
["附表1："]
[" 中央水利投资计划执行定期进度考核评分表（6月底）"]
["被考核单位：_________"]
["序号","考核内容","分值","考核指标","得分计算方法","评分单位","得分","签字/盖章"]
[1,"中央投资计划执行情况（50）",25,"中央投资计划下达","中央投资计划下达率×25","规计司会同有关单位","",""]
[null,null,15,"中央投资到位","中央投资到位率×15",null,""]
[null,null,10,"中央投资计划完成","中央投资计划完成率×10",null,""]
[2,"地方配套投资计划执行情况（50）",25,"地方配套投资计划下达","地方配套投资计划下达率×25",null,""]
[null,null,15,"地方配套投资到位","地方配套投资到位率×15",null,""]
[null,null,10,"地方配套投资计划完成","地方配套投资计划完成率×10",null,""]
["合计",null,100,"","",null,""]
["规计司：\n\n                                                                                                      （盖章）\n                                                                                                  年   月   日"]
["注：1、各考核指标最终得分不能超过该指标分值。"]
["    2、对于水利项目全部为中央补助投资的省份，其地方配套投资执行情况赋分采用其中央投资计划执行情况同样分值。"]
["\u000f"]

{"sheet":"附表2","index":1,"n_rows":15,"n_cols":8,"rows_kept":15,"merged":[[2,0,2,7],[5,0,7,0],[5,1,7,1],[5,5,10,5],[5,7,11,7],[8,0,10,0],[8,1,10,1],[11,0,11,1],[11,4,11,5],[12,0,12,7],[13,0,13,7],[14,0,14,7]],"flags":["formulas_cached_only"]}
[]
["附表2："]
["中央水利投资计划执行定期进度考核评分表（9月底）"]
["被考核单位：_________"]
["序号","考核内容","分值","考核指标","得分计算方法","评分单位","得分","签字/盖章"]
[1,"中央投资计划执行情况（50）",5,"中央投资计划下达","中央投资计划下达率×5","规计司会同有关单位","",""]
[null,null,15,"中央投资到位","中央投资到位率×15",null,""]
[null,null,30,"中央投资计划完成","中央投资计划完成率×30",null,""]
[2,"地方配套投资计划执行情况（50）",5,"地方配套投资计划下达","地方配套投资计划下达率×5",null,""]
[null,null,15,"地方配套投资到位","地方配套投资到位率×15",null,""]
[null,null,30,"地方配套投资计划完成","地方配套投资计划完成率×30",null,""]
["合计",null,100,"","",null,""]
["规计司：          \n\n\n                                                                                                        （盖章）\n                                                                                                     年   月   日"]
["注：1、各考核指标最终得分不能超过该指标分值。"]
["    2、对于水利项目全部为中央补助投资的省份，其地方配套投资执行情况赋分采用其中央投资计划执行情况同样分值。"]

{"sheet":"附表3","index":2,"n_rows":24,"n_cols":8,"rows_kept":24,"merged":[[1,0,1,1],[2,0,2,7],[3,0,3,3],[5,0,6,0],[5,1,6,1],[5,5,8,5],[5,7,8,7],[7,0,8,0],[7,1,8,1],[9,0,19,0],[9,1,19,1],[9,4,19,4],[20,0,20,1],[20,4,20,5],[21,0,21,7],[22,0,22,7],[23,0,23,7]],"flags":["formulas_cached_only"]}
[]
["附表3："]
["中央水利投资计划执行年度综合考核评分表"]
["被考核单位：_________"]
["序号","考核内容","分值","考核指标","得分计算方法","评分单位","得分","签字/盖章"]
[1,"中央投资计划执行情况（40）",10,"中央投资到位","中央投资到位率×10","规计司会同有关单位","",""]
[null,null,30,"中央投资计划完成","中央投资计划完成率×30",null,""]
[2,"地方配套投资计划执行情况（40）",10,"地方配套投资到位","地方配套投资到位率×10",null,""]
[null,null,30,"地方配套投资计划完成","地方配套投资计划完成率×30",null,""]
[3,"日常管理情况（20）",3,"投资计划工作管理情况","有关司局和单位对日常管理各项评分实行百分制，得分90分及以上的为好；80～90分的为较好；80分及以下为差。每项得分乘以相应分值权重为该项最终得分。\n如果某省份目前没有考核内容中涉及的水利项目，则对该省份此类项目日常管理评分以该项目各省份平均分值计。\n","规计司","",""]
[null,null,3,"引调水、枢纽水源、江河治理、新建大型灌区、病险水库（水闸）除险加固等管理情况",null,"建管司","",""]
[null,null,1,"水土保持项目管理情况",null,"水保司","",""]
[null,null,3,"农村饮水安全、灌区改造、泵站改造、规模化节水示范、牧区水利及小型农田水利等管理情况",null,"农水司","",""]
[null,null,1,"水政监察项目",null,"政策法规司","",""]
[null,null,1,"水资源实时监控系统项目",null,"水资源司","",""]
[null,null,2,"水利部稽察涉及的管理情况",null,"安监司","",""]
[null,null,2,"山洪灾害防治、防汛指挥二期、抗旱规划实施等管理情况",null,"防  办","",""]
[null,null,1,"农村水电项目管理情况",null,"水电局","",""]
[null,null,1,"水文建设项目，水利信息化建设项目",null,"水文局","",""]
[null,null,2,"水利部稽察涉及的管理情况",null,"建安中心","",""]
["合计",null,100,"","",null,"",""]
["规计司： \n         \n                                                                                                                                  （盖章）\n                                                                                                                             年   月   日"]
["注：1、各考核指标最终得分不能超过该指标分值。"]
["    2、对于水利项目全部为中央补助投资的省份，其地方配套投资执行情况赋分采用其中央投资计划执行情况同样分值。"]